## Team_5_Internal_Risk_Tracking_L
Risk List (LCAM)
Project Name: |  |  | Aerial Imagery Initiative
Project Manager Name: |  |  | David Tien / Maria Jensen
Project Description: |  |  | Processing aerial imagery (Lidar) to identify flood zones and potentially fire zones.
Resolution | ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan | Raised by
|  | Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
Has never been an issue, the team has worked cohesively together and hopefully will deliver excellent results 27/4/21 | 1 | Closed | High | Low | Closed | The members of G5 not working together cohesively. | Impacts productivity and working relationships. Puts a strain on the whole team. | Project Management | Ill communication, lack of task completion, sloppy work. | After a few incidents (1-2), issues with team members will be dealt with. Team charter outlines further details. | Avoidance | This was a concern in the beginning but it has been proven that the team works. No response strategy needed at this time, but guidelines outlined in the team charter in any case that is ever needed. | The team charter outlines a plan given any issues ever arise with the team. | Patrick (G5)
Positive, the team has access to most of what is needed to move forward. Played out as expected 27/4/21 | 2 | Closed | High | High | Closed | The delays regarding further, more specific information from DCS, Spatial Services are worrying for the team and are pushing the boundaries of deadlines. G5 is now half way (approx.) through the first subject and we are still not entirely sure of the project's specific requirements. | Delays project deadline and impedes overall progress. G5 still has plenty to work on for iteration 2, but we are starting to get annoyed not having greater direction | Schedule | Whilst on top of the major deadlines like LCOM, the team is starting to notice the time slip away in the session with no clear sign of exactly what we are doing and where we are headed. DCS assures us that information is coming and thanking us for our patience. | No triggers other than continuous involvement with David and DCS, waiting for more details and asking as many questions as possible. | Acceptance | Continuous involvement with David and DCS, waiting for more details and asking as many questions as possible. Following up on leads and keeping up with other aspects of work. | None, too far into project. Time damage would be too great, just have to make things work even if there are delays. David (CSU) is aware and understanding given the circumstances. | Patrick (G5)
All students completed AWS Cloud Practitioner Certification 24/05/2021 | 3 | Closed | Medium | Medium | Closed | AWS Cloud Practitioner Certification. All five team members from G5 have to complete the basic intro AWS certification in order to use the DCS AWS environment. Simon, an employee from DCS says this is to ensure we have a sound understanding of the basics including billing and the effects it has. | No DCS system access until this is completed, completing the certification proves that we have a general competency in AWS. | Data/Information | Delays in obtaining this certification can delay time spent understanding and planning with the tools available. | No triggers and no contingency plan, just have to be keep studying and attempting. | Acceptance | Keep attempting the certification until completed. | None. | Patrick (G5)
Neutral, did not meet LCOM deadline but contingency worked as expected 27/4/21 | 4 | Closed | Low | Medium | Closed | Not meeting the LCOM assessment deadline. David has said he would be understanding in the circumstance and offer a slight extension if required. | Delays project timeline. | Schedule | All team members are unavailable to complete all LCOM documents or the team doesn't have enough information to continue. | Any of the symptom events occur. | Contingency | Ask more questions and for an extension if needed. | Request an extension from David to meet the dea | Patrick (G5)
Working locally is helping save on development costs, etc. 19/6/21 | 5 | Closed | High | Medium | Closed | Using AWS and running tests or carrying out general operations attracts a cost. Going over budget is the concern. | Reduces overall budget for the project, this budget is maintained by DCS and they will have budget alarms but can still be a costly exercise. | Life-cycle Costs | AWS budgets alerts are triggered. DCS starts asking questions and will try to understand the costs. | AWS budgets alerts are triggered. | Avoidance | Planning our tests and general operations will minimise the risk of this occurring. Having a solid understanding of the applied resources and their cost will ensure we know what costs / damages may occur. DCS will have budget alerts and cost management systems in place to ensure we don't overspend but it is still really important we manage this well. | If the budgets gets maxed out for unplanned reasons we may be forced to be more theoretical in our approach, less hands on until we have more solid foundations in our planning. Meaning we should be careful the whole way making sure not to max out budgets. | Patrick (G5)
| 6 | Open | High | Medium | Red | Jupyter notebook platform is costly if left running | Reduces overall budget for the project, this budget is maintained by DCS and they will have budget alarms but can still be a costly exercise. | Life-cycle Costs | Notebooks left running past requirement. | If an instance is running and is determined not to be required at the present time implement contingency. | Avoidance | Plan testing and implementation in Jupyter notebooks and make sure they are not left running when not required. | Stop any unrequired instances of Jupyter notebook | Andrew (G5)
The team now has a solid idea for the project and moving forward, it has brought great excitement to be able to get into the project properly. James from Intellify has been a major part of the solution of this front 27/4/21 | 7 | Closed | High | High | Closed | DCS's requirements are tied up in one camp, Leanne from DCS has the specific requirements for the platform but is regularly busy so it is hard to schedule meetings, this can affect team 5's deadlines when more information is required. | Specific requirements are needed to push the project forward, not getting these requirements in a timely manner results in interruptions in team 5's production of planning documents. | Schedule | The team approaches major deadlines with no sign of meetings for requirements gathering. | Specific business requirements are needed and major deadlines are approaching. | Acceptance | When information is need from Leanne, many questions should be compiled and answered in one go to ensure another meeting does not need to be arranged within a short period of the last. Notice is key. Meetings will more than likely be scheduled by someone from DCS ie Maria Jensen or Intellify. | Schedule meetings with the other parties involved to see if the questions can be answered there first. | Patrick (G5)
Never became as issue, nor did it need to be followed up on. 19/6/21 | 8 | Closed | Low | Low | Closed | Per pixel processing when working with ML and then converting it to Vector can take large time amounts of time and still may require an interesting / complex solution. | May require a specific method of processing to avoid this risk area. | Technology | NA | Design and planning will highlight possible areas of concern with this. | Avoidance | To be decided after further planning. May not even need to be considered. | NA | Intellify
| 9 | Open | High | Medium | Red | Project could be of a high complexity, the team is covering the extra distance for knowledge but the complexity could cause issues. | Could create additional delays as learning and consultation is needed to continue moving forward. May not make major deadlines in time and may not be feasible, workarounds would be required. | Feasibility | Delays, confusion and frustration regarding various aspects of the project. | Large tasks, out of scope requests from DCS | Mitigation | Plan meticulously and declare out of scope activities, if there is resistance from DCS or Intellify in terms of asking more than reasonable, this becomes a issue that has to be raised with David. | Find work arounds for difficult tasks. | Patrick (G5)
Nik from Intellify helped explore Davids points of traditional image indentification techniques, alleviating issues for team 5. 1/5/21 | 10 | Closed | High | High | Closed | Davids lack of guidance and clarity in his requests / propositions, this relates to his inexperience with AWS (does not know the relevant systems that replicant traditional imaging processing methodologies) | This is a major risk and is doing some significant damage to the team's time, morale and focus towards to the project. | Project Management | Stressed and confused team. | Meetings | Mitigation | Discussion of concepts and ideas relating to Davids information provided or expressed. | Mitigation only. | Patrick (G5)
| 11 | Open | Low | Medium | Green | Partial attendance for the technical meetings with Nik / DCS on Fridays derails the the technical productivity of group 5, DCS and Intellify. | Slower training and uptake of technical processes / skills for team 5 overall. Slows down Intellifys involvement with team 5. | Project Management | Slower meeting, not as much to be gained overall for the team. | More than one team member not attending the technical meeting. | Avoidance | Discussion with the team to confirm that the time slot suits, if it does not then proceed with contingency. | Move the meeting again to a time that works for everyone. | Nik (Intellify) / Patrick (G5)
| 12 | Closed | Low | Medium | Closed | Computation / processing time is greater than turnaround window (window time TBA). | This risk could mean the failure to produce a working set of flood regions within the alloted time window for data to be shipped out to emergency services, etc. | Technology | Delays in processing times when using AWS sagemaker as the compute platform for the notebooks. | Same as symptoms (the symptoms trigger the risk) | Contingency | Test different OpenCV algorithms and find the ones that work best and require less processing time. | Work locally, prove concept is possible then test AWS has the capacity at the resource level that is being implemented (ml.t3.medium, etc) | Patrick (G5)
| 13 | Closed | Low | High | Closed | Certain existing modules of AWS do not provide a great result for image processing in our case as pointed out by Nik from Intellify, as such we experimenting with OpenCV.Hoping it will herald the results required. | Imcomplete solutions to be created from the AWS platform resources. | Technology | The results from the AWS system may not be as accurate or as desired, specifically not meeting the requirements of the project, thus needing an alternative method. | Results from using AWS platform systems aren't meeting the project requirements. | Avoidance | Using third party libraries and systems (where possible, approprate, licensed approved, etc) or research other systems AWS has available / is compatible with. | Same as response strategy. | Patrick (G5)
| 14 | Open | Medium | High | Yellow | Indentifying islands, trees and areas that are incorrectly included or excluded from the flood area. Ie labelling tree tops that cover flood area as not flood, when it is actually part of the flood. | Can affect indentified flood area. Depending on size of error could result in a large diffrence to flood extent | Data/Information | [5 empty] | Adam (G5)
| 15 | Open | Medium | Medium | Yellow | Translating image coordinates into real world coordinates. Is the distance linear or does the image geoid/curvature correction? | Will resullt in inaccurate translation between image data and eventual GIS input | Data/Information | [5 empty] | Adam (G5)
| 16 | Open | High | Medium | Yellow | Testing / training data set not very wide, currently with 2 images sets. To account for more variations additional image sets will be required. | End system may only be effective on data sets used during development. New imagery may be incompatable with delivered system. | Overall Project Failure | [5 empty] | Adam (G5)
| 17 | Open | High | Medium | Red | Technical aspects take time to implement, which can become extremely time consuming for Team 5. Team 5 have other subjects, adding potential strain the quality and volume of work. | Impact to the quantity and quality of work produced | Schedule | Stressed team with slower progress | Falling behind schedule | Mitigation | Maintain a schedule and continue with to work with manageable portions each week, as Nik as outlined in his emails. | Reconsider which student tasks sit with, in an attempt to cover all requirements and distribute workload to work around schedules. | Team (All of G5)
| 18 | Open | Medium | Medium | Yellow | Team 5 has had to step up their tier of SageMaker instances, from ml.t3.medium to ml.t3.large, as guided by Nik and his implementations. | ml.t3.large costs $0.127/hour, effectively doubling running costs. | Life-cycle Costs | Increasing costs |  | Avoidance | Only increase costs where absolutely required and always within reason. | Mitigation only | Team (All of G5)
| 19 | Open | Medium | Medium | Yellow | Processing larger images with low memory allocations is extremely difficult and encounters constant crashing/failures; we haven't yet dealt with some of the bigger image types. | Larger images (over 1GB) will overload the current system, though this is currently untested. | Project Resources | System failing due to exceedingly high load |  | Mitigation | Increase SageMaker instances sizes or implement automatic/manual resizing depending on the size of images that need processing. | Mitigation only | Team (All of G5)
| 20 | Open | High | Medium | Red | Varied image classiication results could skew overall effect of the Machine Learning model. Incorrectly identified elements will also have the same effect. | Machine Learning could be impacted, meaning more time may be required to explore other areas, make corrections and deal with issues as they arise. | Feasibility | Machine Learning encountering unexpected areas may not be adequately prepared. | Machine Learning failing to correctly highlight features of an area image. | Avoidance | Discuss internally and determine with current resources, best plan to avoid. | To be discussed | Team (All of G5)

## Instructions
Risk List (LCAM)
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources